## Gantt Chart
GANTT CHART TEMPLATE - Team Aspire - NBA DATABASE
| TASK NAME | START DATE | END DATE | DURATION (WORK DAYS) | TEAM MEMBER | WEEK 7 | [6 empty] | WEEK 8 | [6 empty] | WEEK 9 | [6 empty] | WEEK 10 | [6 empty] | WEEK 11 | [6 empty] | WEEK 12 | [6 empty] | WEEK 13 | [6 empty] | WEEK 14 | [6 empty] | WEEK 15
[6 empty] | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su
BASIC FEATURES
| Coding Basic menu in Python | 2019-03-01 |  | 1 | Adeel | bar: WEEK 8 F; WEEK 10 F to WEEK 10 Su
| Taking in files | 2019-03-01 |  | 1 | Michael | bar: WEEK 8 F; WEEK 10 F to WEEK 10 Su
| Getting statistics | 2019-03-01 |  | 1 | Bashaar | bar: WEEK 8 F; WEEK 10 F to WEEK 10 Su
MEDIUM
| Designing GUI | 2019-03-04 |  | 3 | Adeel | bar: WEEK 8 M to WEEK 9 W; WEEK 10 F to WEEK 10 Su
| Desiging the Database | 2019-03-04 |  | 3 | Michael | bar: WEEK 8 M to WEEK 9 W; WEEK 10 F to WEEK 10 Su
| Win Predictor | 2019-03-04 |  | 3 | Bashaar | bar: WEEK 8 M to WEEK 9 W; WEEK 10 F to WEEK 10 Su
Fourth Sample
| Combine GUI and Code and Database | 2019-03-15 |  | 5 | Adeel/Michael | bar: WEEK 8 M to WEEK 8 Su; WEEK 10 F to WEEK 11 T
| Clean code and organize file and push to repository | 2019-03-15 |  | 5 | Bashaar | bar: WEEK 8 M to WEEK 8 Su; WEEK 10 F to WEEK 11 T